## UX Findings
IndusJS Fleet — UX & User Flow Enhancement Analysis
40+ screens analyzed across 13 feature modules • Deep code-level UX audit • Prioritized by severity & user impact
S.No | Module / Screen | Finding | Severity | Category | Current Behavior | Recommended Fix | Impact on User | Effort | Status
Cross-Cutting / Architecture (15 findings)
1 | Cross-Cutting / Architecture | No scroll on form screens | Critical | Accessibility | Login, ForgotPassword, ChangePassword have no verticalScroll modifier | Add Modifier.verticalScroll(rememberScrollState()) to all form Column layouts | Soft keyboard obscures fields; users cannot reach submit button on small screens | Low | Open
2 | Cross-Cutting / Architecture | No unsaved changes warning on ANY form | Critical | User Flow | All create/edit forms (AddVehicle, CreateDriver, CreateTrip, CreateCustomer, AddPayment, CreateTeamMember, AddPurchaseInfo, all edit modes) lose data on back press | Add a shared 'DiscardChangesDialog' shown via BackHandler when form hasChanges == true | Users lose significant form data accidentally — high frustration especially on long forms like CreateTrip | Medium | Open
3 | Cross-Cutting / Architecture | No pull-to-refresh gesture on list screens | High | Interaction | VehiclesList, DriversList, TripsList, PaymentsList, FinanceList have toolbar refresh button only; no swipe gesture despite isRefreshing in state | Wrap content with PullToRefreshBox (M3) or pullToRefresh modifier — TeamListScreen already implements this correctly | Users expect pull-to-refresh on mobile; toolbar-only refresh is non-discoverable | Low | Open
4 | Cross-Cutting / Architecture | No delete confirmation on list screens | High | User Flow | VehiclesScreen and DriversScreen fire delete intent directly without confirmation dialog | Add AlertDialog with warning text before executing delete — PaymentDetail already has this pattern | Accidental data deletion with no undo | Low | Open
5 | Cross-Cutting / Architecture | Emoji icons instead of Material Icons | High | Consistency | SignUp, ForgotPassword, ChangePassword use emoji (🔒,👁️) for password fields; Dashboard nav drawer uses emoji; cost entries use ⛽📏; Reports use 🔍📄 | Replace all emoji with proper Material Icon drawables from ijs-ui-components-lib. LoginScreen already uses FleetPasswordField with proper icons | Inconsistent rendering across Android/iOS/Web; accessibility issues (screen readers); unprofessional appearance | Medium | Open
6 | Cross-Cutting / Architecture | Hardcoded strings break i18n | High | Internationalization | Dashboard has 50+ hardcoded strings; Profile edit mode; all Report screens; Maps screen. AlertsListScreen is the exemplar using stringResource() everywhere | Audit all screens and move hardcoded strings to commonMain/composeResources/values/strings.xml using stringResource() | App cannot be localized to any other language; inconsistent with i18n-ready screens | High | Open
7 | Cross-Cutting / Architecture | Hardcoded colors instead of theme tokens | High | Theming | Dashboard, TripCostEntry, all Report screens use hardcoded hex like Color(0xFF4CAF50), Color(0xFFEF4444). Two competing greens (0xFF10B981 vs 0xFF4CAF50) and reds | Create FleetColors object in ijs-ui-components-lib with semantic tokens (profitGreen, lossRed, warningAmber) or extend MaterialTheme | Colors won't adapt to dark mode or dynamic theming; visual inconsistency between screens | Medium | Open
8 | Cross-Cutting / Architecture | Inconsistent back button implementation | Medium | Navigation | ProfileScreen uses ic_arrow_back drawable; ForgotPassword/ChangePassword use Text('←'); LoginScreen has none (correct) | Standardize on Icon(painterResource(Res.drawable.ic_arrow_back)) for all back buttons | Visual inconsistency disrupts user's mental model of navigation | Low | Open
9 | Cross-Cutting / Architecture | No shimmer/skeleton loading anywhere | Medium | Perceived Performance | All loading states use simple CircularProgressIndicator. No skeleton placeholders for data-rich screens | Create FleetShimmerPlaceholder composable in ijs-ui-components-lib for card, list-item, and detail layouts | Abrupt content pop-in; perceived slowness compared to modern apps | High | Open
10 | Cross-Cutting / Architecture | Orphaned CoroutineScopes in ViewModels | Critical | Bug | VehicleDetailViewModel and DriverDetailViewModel use CoroutineScope(dispatcherProvider.main).launch instead of viewModelScope | Replace with viewModelScope.launch or the MviViewModel's built-in scope | Memory leaks; coroutines survive ViewModel disposal; potential crashes | Low | Open
11 | Cross-Cutting / Architecture | collectAsState vs collectAsStateWithLifecycle inconsistency | Medium | Lifecycle | AddVehicleScreen uses collectAsState(); all other screens use collectAsStateWithLifecycle() | Standardize on collectAsStateWithLifecycle() across all screens | State collection continues when app is backgrounded, wasting resources | Low | Open
12 | Cross-Cutting / Architecture | Weak email validation everywhere | Medium | Validation | SignUp, Profile edit, Team create all use contains('@') && contains('.') which accepts @. as valid | Use a proper email regex pattern in ValidationUtils.isValidEmail() and reference it everywhere | Invalid emails accepted, causing API errors or delivery failures | Low | Open
13 | Cross-Cutting / Architecture | Hardcoded year bounds (2026, 2030) | Medium | Time Bomb | AddVehicleVM line 106 rejects year > 2026; VehicleDetailVM says 'between 1900 and 2030' | Use Clock.System.now().toLocalDateTime(...).year + 1 for dynamic upper bound | Will start rejecting valid vehicle years in 2027/2031 | Low | Open
14 | Cross-Cutting / Architecture | Default role escalation on error | Critical | Security | TeamListViewModel defaults to 'owner' role when getUserRole() fails, granting maximum permissions | Default to 'supervisor' (least-privileged) on role fetch failure | Security vulnerability: error condition grants admin access | Low | Open
15 | Cross-Cutting / Architecture | No FleetTopAppBar shared component | Medium | Consistency | Every screen manually creates TopAppBar with different colors (surface vs primary), icon tinting, and back button patterns | Create FleetTopAppBar in ijs-ui-components-lib standardizing surface background, icon tinting, and back navigation | Inconsistent app bar appearance when navigating between screens (especially Reports sub-screens) | Medium | Open
Authentication & Profile (6 findings)
16 | Authentication & Profile | Dual error display on Login | Medium | User Feedback | LoginScreen shows error both inline (state.error Text) AND via snackbar (Effect.ShowError) | Pick one: inline for field-level, snackbar for API-level. Don't show both for same error | Confusing double-error display | Low | Open
17 | Authentication & Profile | No password strength indicator | Low | Form UX | SignUp and ChangePassword show no strength meter | Add a PasswordStrengthIndicator composable below password field (weak/medium/strong with color bar) | Users create weak passwords; no guidance on security | Medium | Open
18 | Authentication & Profile | SignUp sequential validation | Medium | Form UX | Shows first error only; user must fix and re-submit to see next error | Validate all fields simultaneously and show all errors at once with isError on each field | Multiple submit attempts needed to fix all errors; frustrating | Low | Open
19 | Authentication & Profile | No logout confirmation | Medium | User Flow | ProfileScreen logout navigates immediately without confirmation dialog | Add AlertDialog: 'Are you sure you want to logout?' | Accidental logout loses unsaved state across all screens | Low | Open
20 | Authentication & Profile | Profile loading has no skeleton | Low | Perceived Performance | Simple spinner while complex card layout loads | Add shimmer placeholder matching card layout | Abrupt transition from spinner to rich content | Medium | Open
21 | Authentication & Profile | Snackbar races with NavigateBack | Medium | Bug | ChangePassword fires ShowSnackbar then NavigateBack sequentially; snackbar may not render before navigation | Show snackbar on the PREVIOUS screen after navigation, or use a longer delay, or switch to a Toast | User never sees success feedback message | Low | Open
Dashboard (4 findings)
22 | Dashboard | Navigation drawer shows no selected state | Medium | Navigation | All drawer items have selected = false | Track current route and set selected = true on matching drawer item | Users can't tell which section they're in from the drawer | Low | Open
23 | Dashboard | Timezone hardcoded to IST | Medium | Bug | Greeting uses (hourOfDay + 5) % 24 — hardcoded UTC+5 offset | Use kotlinx-datetime TimeZone.currentSystemDefault() for correct local time | Wrong greeting for users outside IST timezone | Low | Open
24 | Dashboard | No deep link support | Low | Navigation | No deepLinks configured on any FleetRoute despite @Serializable support | Add deepLinks to key routes (VehicleDetail, TripDetail, PaymentDetail) for notification tap-through | Users can't open specific items from notifications or shared links | High | Open
25 | Dashboard | Offline dismiss button too small | Low | Accessibility | OfflineBanner dismiss icon is 18dp in 32dp target; recommended minimum is 48dp | Increase IconButton size to 48dp or use Modifier.minimumInteractiveComponentSize() | Hard to tap dismiss on offline banner | Low | Open
Onboarding (2 findings)
26 | Onboarding | No previous/back button | Low | Navigation | Users can swipe back but no explicit Previous button for discoverability | Add a 'Previous' text button alongside 'Next' on non-first pages | Users who don't know swipe may feel stuck | Low | Open
27 | Onboarding | iconRes typed as Any (unsafe) | Low | Code Quality | OnboardingPage.iconRes is Any, cast with @Suppress('UNCHECKED_CAST') | Type as DrawableResource directly | Potential ClassCastException at runtime | Low | Open
Vehicles (6 findings)
28 | Vehicles | No pagination on VehiclesList | High | Scalability | All vehicles loaded at once in single API call | Implement infinite scroll pagination (same pattern as CustomersListScreen) | Performance degradation with large fleets (100+ vehicles) | Medium | Open
29 | Vehicles | Refresh race condition in ViewModel | Medium | Bug | refreshVehicles() sets isRefreshing=false before loadVehicles() flow completes | Move isRefreshing=false inside the flow collection onCompletion or use finally block | Refresh indicator disappears before data is actually updated | Low | Open
30 | Vehicles | VehicleDetailScreen is 3248 lines | High | Maintainability | Single composable file manages 6 tabs + edit mode + overlays | Decompose into per-tab files: OverviewTab.kt, TripsTab.kt, CostsTab.kt, RouteTab.kt, DocsTab.kt, HistoryTab.kt | Extremely difficult to review, test, and maintain | High | Open
31 | Vehicles | VehicleDetail State has 60+ fields | Medium | Architecture | Single monolithic State class for 6 tabs causes unnecessary recompositions | Split into per-tab sub-states or use separate State sealed classes per tab | UI jank from unnecessary recompositions when unrelated state changes | High | Open
32 | Vehicles | Simulated upload progress misleads users | Medium | User Feedback | AddVehicle upload progress uses delay(50) loop; file only uploads on final submit | Either upload immediately on file selection (with real progress) or remove the progress bar and show a 'staged' badge | Users think file is uploaded when it's only staged locally | Low | Open
33 | Vehicles | Expand/collapse icon doesn't rotate | Low | Visual | MaintenanceCostEntry row chevron shows same icon for both states | Apply Modifier.rotate() animation: 0° collapsed → 90° expanded | Users can't visually tell if a cost row is expanded or collapsed | Low | Open
Drivers (5 findings)
34 | Drivers | No pagination on DriversList | High | Scalability | All drivers loaded at once | Implement infinite scroll pagination matching CustomersListScreen pattern | Performance degradation with many drivers | Medium | Open
35 | Drivers | Inaccurate date arithmetic | Medium | Bug | DriverDetailScreen and CreateDriverVM use days/365.25 and days/30 approximations for date parsing | Replace with kotlinx-datetime Instant.fromEpochMilliseconds().toLocalDate() throughout | Wrong dates displayed; DOB validation off by days | Low | Open
36 | Drivers | Dual tab state source of truth | Medium | Bug | DriverDetailScreen has local 'var selectedTab by remember' AND state.selectedTab in ViewModel | Remove local selectedTab; use only ViewModel state for tab selection | Tab state can desync between local and ViewModel, causing UI glitches | Low | Open
37 | Drivers | isDeleting flag unused in UI | Low | User Feedback | DriversScreen has isDeleting in state but no loading overlay during deletion | Show a loading overlay or disable interactions while delete API call is in progress | User can interact with stale data during delete | Low | Open
38 | Drivers | Deprecated DriverCostsSummaryCard in code | Low | Code Quality | Dead code still in DriverDetailScreen file | Remove deprecated composable | Code bloat, confusion for developers | Low | Open
Trips (7 findings)
39 | Trips | CreateTrip form is very long (7+ sections) | High | Form UX | Single scrollable form with Schedule, Vehicle, Route, Cargo, Priority, Customer, Pricing, Notes sections | Convert to a multi-step wizard (like AddVehicle's 2-step approach) or use collapsible sections | Overwhelming form; high abandonment risk especially on mobile | High | Open
40 | Trips | No draft saving for CreateTrip | High | User Flow | If user navigates away from CreateTrip, all entered data is lost | Implement auto-save draft to local storage (Room or multiplatform-settings) | Users lose complex form data on interruptions (calls, notifications) | High | Open
41 | Trips | No pagination on TripsList | High | Scalability | All trips loaded at once | Implement infinite scroll pagination | Performance degradation with trip history growth | Medium | Open
42 | Trips | Filter chips don't show counts per status | Medium | Information Density | Status filter chips show label only (e.g., 'Planned', 'Completed') | Add count badge: 'Planned (5)', 'Completed (12)' — same pattern as AlertsListScreen | Users can't assess data distribution without tapping each filter | Low | Open
43 | Trips | Edit mode loses scroll position | Medium | User Flow | Entering edit mode on TripDetail replaces content entirely | Preserve scroll position and animate transition between view/edit states | Disorienting jump to top when entering/exiting edit mode | Medium | Open
44 | Trips | Trip cost entry uses hardcoded colors | Low | Theming | TripDetailsCard uses Color(0xFF4CAF50) instead of theme | Use MaterialTheme.colorScheme tokens | Won't adapt to dark mode | Low | Open
45 | Trips | delay(500) for pre-select trip | Low | Bug | TripCostEntryVM uses delay to wait for data before pre-selecting trip | Use LaunchedEffect triggered by trips list state change instead of arbitrary delay | May fail on slow connections; race condition | Low | Open
Customers (5 findings)
46 | Customers | Search field uses raw OutlinedTextField | Medium | Consistency | CustomersListScreen uses OutlinedTextField; TripsList and VehiclesList use FleetSearchField | Replace with FleetSearchField for consistent look and behavior | Different search bar appearance and behavior across list screens | Low | Open
47 | Customers | canViewFinancials hardcoded to true | High | Security | CustomerDetailScreen line: canViewFinancials = true with TODO comment | Read role from userLocalDataSource and enforce Owner/GM-only access | All roles can see financial data meant only for Owner/GM | Low | Open
48 | Customers | No status filter chips on CustomersList | Medium | Feature Gap | CustomersList has search only; no Active/Inactive filter chips | Add filter chips matching VehiclesList/DriversList/TripsList pattern | Users can't quickly filter by customer status | Low | Open
49 | Customers | Status toggle has no confirmation | Medium | User Flow | CustomerDetail status Switch toggles immediately without confirmation | Add confirmation dialog: 'Deactivate this customer?' | Accidental status change for important customers | Low | Open
50 | Customers | Edit mode resets to Overview tab | Low | User Flow | Canceling edit on CustomerDetail resets tab to Overview regardless of which tab user was on | Restore previous tab selection on edit cancel | Disorienting tab jump after cancel | Low | Open
Payments (6 findings)
51 | Payments | Long-press delete is broken | High | Bug | onLongClick parameter is @Suppress('UNUSED_PARAMETER'); only Modifier.clickable is used, not combinedClickable | Wire onLongClick using Modifier.combinedClickable for delete action | Delete from flat list view is impossible; feature is dead code | Low | Open
52 | Payments | Duplicate save button on AddPayment | Medium | UI Clarity | Save icon in toolbar AND full-width button at bottom | Remove toolbar save; keep only the prominent bottom button (standard mobile pattern) | Confusing which button to press; inconsistent with form screen patterns | Low | Open
53 | Payments | QuickFill buttons not rendered | Medium | Missing Feature | QuickFillFull and QuickFillHalf intents exist in contract; ViewModel handles them; no UI buttons | Add 'Full Amount' and 'Half Amount' quick-fill chips above the amount field | Users must manually calculate and type payment amounts | Low | Open
54 | Payments | Filter buried in overflow menu | Medium | Discoverability | Payment filters require: tap overflow → tap Filter → bottom sheet. Two taps to reach filters | Add a filter icon directly in the toolbar or use persistent filter chips below search | Low discoverability of powerful filter functionality | Low | Open
55 | Payments | Duplicate download receipt button | Low | UI Clarity | PaymentDetail has download icon in toolbar AND in overflow menu | Remove one; prefer toolbar icon for primary action | Confusing redundancy | Low | Open
56 | Payments | downloadReceipt() is a TODO stub | Low | Dead Code | ViewModel shows 'coming soon' toast but screen already has working PDF export | Remove the dead DownloadReceipt intent/effect; clean up ViewModel | Code confusion; inconsistent behavior paths | Low | Open
Team Management (5 findings)
57 | Team Management | Delete uses full loading state | Medium | User Feedback | deleteTeamMember sets isLoading=true replacing entire list with LoadingContent | Use per-item loading indicator or transparent overlay | Entire list disappears during delete; jarring visual disruption | Low | Open
58 | Team Management | Reset password dialog dismisses too early | Medium | Bug | showResetPasswordDialogForMemberId set to null immediately; dialog closes before API completes | Keep dialog open with a loading spinner until API response; then close | No visual feedback that password reset is in progress | Low | Open
59 | Team Management | No per-field error indicators on CreateTeamMember | Medium | Form UX | All validation errors go to a single error card; individual fields don't show isError | Add isError + supportingText to each field (same as CreateDriverScreen pattern) | Users must read error card then find the problematic field; slow error recovery | Low | Open
60 | Team Management | Password visibility uses emoji toggle | Low | Accessibility | CreateTeamMember uses 👁️/👁️‍🗨️ emoji for password visibility | Use Icon(Icons.Outlined.Visibility / VisibilityOff) with proper contentDescription | Screen readers announce emoji name; inconsistent rendering across platforms | Low | Open
61 | Team Management | Legacy TeamMemberCard still in code | Low | Code Quality | 'Legacy (kept for backward compatibility)' wrapper components that just delegate | Remove legacy wrappers; use Enhanced versions directly | Code bloat; developer confusion | Low | Open
Vehicle Finance (7 findings)
62 | Vehicle Finance | Monolithic shared ViewModel for 4 screens | High | Architecture | VehicleFinanceViewModel manages list, detail, add purchase, and record payment with ~100 state fields | Split into per-screen ViewModels (FinanceListVM, FinanceDetailVM, AddPurchaseVM) | State changes in one screen cause recompositions in all others; hard to reason about | High | Open
63 | Vehicle Finance | N+1 API query problem | High | Performance | loadPurchaseInfoForVehicles makes separate API call per vehicle in a for loop | Create a batch endpoint or parallel coroutine execution with async/awaitAll | 50 vehicles = 50 sequential API calls; extremely slow initial load | Medium | Open
64 | Vehicle Finance | Dead 'Export PDF Report' button | Medium | Dead Code | VehicleFinanceDetailScreen has a button with onClick = { /* TODO: Export PDF */ } that does nothing; working PDF exists in toolbar | Remove the dead button or wire it to the existing PDF export | Users tap a button that does nothing; loss of trust | Low | Open
65 | Vehicle Finance | Not Recorded cards not fully tappable | Medium | Interaction | PENDING vehicle cards use Modifier (no-op) — only the 'Add Info' button is clickable | Make entire card clickable to navigate to AddPurchaseInfo | Reduced tap target; unexpected behavior vs other cards | Low | Open
66 | Vehicle Finance | Duplicate add button (toolbar + FAB) | Low | UI Clarity | Add icon in toolbar AND ExtendedFloatingActionButton | Remove toolbar add; keep only FAB (standard Material pattern) | Confusing redundancy | Low | Open
67 | Vehicle Finance | getNextEmiDueDate duplicated across 2 files | Low | Code Quality | Same function copy-pasted in VehicleFinanceScreen and VehicleFinanceDetailScreen | Extract to shared utility in the finance module | Maintenance burden; risk of divergence | Low | Open
68 | Vehicle Finance | No EMI recording CTA in EmiPaymentHistory | Medium | User Flow | EmiPaymentHistory is read-only; user must navigate back to detail to record payment | Add a 'Record EMI Payment' FAB or button on this screen | Breaks user flow; extra navigation steps for common action | Low | Open
Reports (7 findings)
69 | Reports | Snackbar effects silently dropped | Critical | Bug | ReportsScreen handlers: 'is Effect.ShowSnackbar -> {}' — all snackbar/export effects consumed but never displayed | Wire SnackbarHostState and show messages in LaunchedEffect (same as every other screen) | User gets zero feedback on errors and export results | Low | Open
70 | Reports | VehicleProfitLossScreen is 2841 lines | High | Maintainability | Massive file with Fleet Overview + Single Vehicle + Charts + Filter Sheets all in one | Decompose into FleetOverviewContent.kt, SingleVehiclePLContent.kt, VehicleFilterSheet.kt, PLChartComponents.kt | Unmaintainable; impossible to review in code review | High | Open
71 | Reports | Custom error/loading components duplicate shared library | High | Consistency | ReportsScreen, VehiclePLScreen, TripPLScreen all create private LoadingContent/ErrorContent instead of using shared components | Replace all custom implementations with shared LoadingContent, ErrorContent, EmptyContent — AlertsListScreen is the exemplar | Inconsistent error/loading UI between report screens and rest of app | Medium | Open
72 | Reports | No empty state after report generation | Medium | User Feedback | CostAnalysis and ConsolidatedPL show nothing when report returns empty results | Show EmptyContent with 'No data for selected period' message and suggestion to adjust date range | Users think the app is broken when generation succeeds but shows nothing | Low | Open
73 | Reports | Inconsistent TopAppBar colors across report screens | Medium | Consistency | ReportsHub uses surface; CostAnalysis/ConsolidatedPL use primary; VehiclePL uses surface | Standardize on surface background (or create FleetTopAppBar shared component) | Jarring color change when navigating between report sub-screens | Low | Open
74 | Reports | Nested scrollable containers in TripPL | Medium | UX Anti-pattern | verticalScroll Column inside LazyColumn with heightIn(max=300.dp) constraint | Use LazyColumn items directly or a non-scrollable Column with fixed height | Scroll gesture conflicts; confusing scroll behavior | Low | Open
75 | Reports | exportToPdf is a stub in ReportsViewModel | Low | Dead Code | Hardcodes '/sdcard/IndusJSFleet/reports/report.pdf' — Android-specific, non-functional | Implement using ijs-pdf-report module or remove stub | Feature appears available but doesn't work | Low | Open
Maps (4 findings)
76 | Maps | Map is entirely placeholder | Critical | Missing Feature | Map area shows emoji 🗺️ + 'Integration with map SDK required' text. ViewModel uses hardcoded mock data | Integrate platform-specific map SDK (Google Maps for Android, MapKit for iOS, Leaflet for Web) via expect/actual | Core feature (real-time tracking) is non-functional | Very High | Open
77 | Maps | Vehicle list has no search/filter | Medium | Feature Gap | All vehicles shown in flat list with no way to search or filter | Add search field and status filter chips (Moving/Stopped/Offline) | Hard to find specific vehicle in large fleets | Low | Open
78 | Maps | Auto-refresh reads stale state | Medium | Bug | while(state.isLiveTrackingEnabled) captures initial delegate value; won't react to toggle | Use snapshotFlow { state.isLiveTrackingEnabled }.collectLatest for reactive observation | Live tracking toggle may not actually stop/start refresh | Low | Open
79 | Maps | Bottom vehicle panel is not draggable | Low | Interaction | Fixed heightIn(max=300dp) with decorative handle bar that doesn't drag | Use BottomSheetScaffold or DraggableAnchors for a proper draggable panel | Handle bar creates false affordance; users expect drag behavior | Medium | Open
Alerts (3 findings)
80 | Alerts | Dismiss is client-side only | High | Data Persistence | dismissAlert removes from local list; no API call. Dismissed alerts reappear on refresh | Implement server-side dismiss API or persist dismissed IDs locally in Room/Settings | Dismissed alerts keep reappearing; frustrating repetitive dismissals | Medium | Open
81 | Alerts | No action on alert tap | Medium | Navigation | Tapping alert card does nothing; can only dismiss | Navigate to related entity (vehicle detail for doc expiry, driver detail for license expiry) | Users see alert but can't easily act on it — must manually navigate to the entity | Medium | Open
82 | Alerts | No sort options | Low | Feature Gap | Alerts unsortable; displayed in API order | Add sort by: Priority (Critical first), Days Remaining, Entity Name | Users can't prioritize which alerts to address first | Low | Open
Shared UI Components (5 findings)
83 | Shared UI Components | No pull-to-refresh wrapper component | Medium | Missing Component | Each screen must manually implement pull-to-refresh; most don't. Only TeamListScreen does it correctly | Create FleetPullToRefreshBox wrapper in ijs-ui-components-lib | Inconsistent refresh behavior across screens | Medium | Open
84 | Shared UI Components | No FleetSnackbarHost pattern | Low | Missing Component | Each screen manually wires SnackbarHostState + LaunchedEffect; ReportsScreen forgot to wire it | Create FleetScaffold or FleetSnackbarEffect utility that auto-wires snackbar to MVI effects | Boilerplate duplication; easy to forget wiring (proven by ReportsScreen bug) | Medium | Open
85 | Shared UI Components | No reusable Filter Chip Row | Low | Missing Component | Horizontal scrolling filter chips duplicated across 6+ screens with slight variations | Create FleetFilterChipRow<T> with chip labels, counts, selection callback | Code duplication; inconsistent chip styling between screens | Medium | Open
86 | Shared UI Components | No shimmer placeholder component | Low | Missing Component | No skeleton/shimmer loading exists in the library | Create FleetShimmerPlaceholder with card, list-item, and detail presets | All screens use basic spinner; perceived performance is worse than modern apps | High | Open
87 | Shared UI Components | ScreenContent<T> wrapper exists but unused | Low | Underutilization | CommonComponents.kt has ScreenContent<T> that handles loading/error/empty/data but NO screen uses it | Adopt ScreenContent<T> in simpler screens (AlertsList, CustomersList, TeamList) to reduce boilerplate | Every screen re-implements the same loading/error/empty branching manually | Medium | Open

## Summary by Module
Module | Total | Critical | High | Medium | Low
Cross-Cutting / Architecture | 15 | 4 | 5 | 6 | 0
Authentication & Profile | 6 | 0 | 0 | 4 | 2
Dashboard | 4 | 0 | 0 | 2 | 2
Onboarding | 2 | 0 | 0 | 0 | 2
Vehicles | 6 | 0 | 2 | 3 | 1
Drivers | 5 | 0 | 1 | 2 | 2
Trips | 7 | 0 | 3 | 2 | 2
Customers | 5 | 0 | 1 | 3 | 1
Payments | 6 | 0 | 1 | 3 | 2
Team Management | 5 | 0 | 0 | 3 | 2
Vehicle Finance | 7 | 0 | 2 | 3 | 2
Reports | 7 | 1 | 2 | 3 | 1
Maps | 4 | 1 | 0 | 2 | 1
Alerts | 3 | 0 | 1 | 1 | 1
Shared UI Components | 5 | 0 | 0 | 1 | 4
TOTAL | 87 | 6 | 18 | 38 | 25

## Priority Action Plan
Priority | Action Item | Screens Affected | Effort | Impact
P0 | Fix orphaned CoroutineScopes → use viewModelScope | VehicleDetailVM, DriverDetailVM | Low | Prevents memory leaks and potential crashes
P0 | Wire snackbar effects in ReportsScreen (currently silently dropped) | ReportsScreen | Low | Users get zero feedback on errors/exports
P0 | Fix default role escalation: supervisor instead of owner on error | TeamListViewModel | Low | Security vulnerability granting admin access on error
P0 | Add verticalScroll to Login, ForgotPassword, ChangePassword forms | 3 auth screens | Low | Forms unusable when keyboard is open on small screens
P1 | Add confirmation dialogs for all destructive actions (delete/logout) | VehiclesList, DriversList, ProfileScreen | Low | Prevents accidental data loss
P1 | Add unsaved changes warning (DiscardChangesDialog) to all forms | 10+ form screens across all modules | Medium | Prevents accidental data loss on complex forms
P1 | Implement pull-to-refresh across all list screens | VehiclesList, DriversList, TripsList, PaymentsList, FinanceList, CustomersList | Medium | Standard mobile UX expectation; currently non-discoverable refresh
P1 | Replace emoji icons with proper Material Icons throughout | SignUp, ForgotPassword, ChangePassword, Dashboard nav, cost entries, reports | Medium | Consistent rendering, proper accessibility, professional appearance
P1 | Fix canViewFinancials hardcoded to true in CustomerDetail | CustomerDetailScreen | Low | Security: all roles can see Owner/GM-only financial data
P1 | Fix long-press delete (broken combinedClickable) in PaymentsList | PaymentsScreen | Low | Delete from flat list view is completely broken
P2 | Add pagination to Vehicle, Driver, Trip list screens | VehiclesList, DriversList, TripsList | Medium | Performance at scale; CustomersList already has infinite scroll
P2 | Decompose mega-files: VehicleDetail (3248 lines), VehiclePL (2841 lines) | VehicleDetailScreen, VehicleProfitLossScreen | High | Maintainability and code review feasibility
P2 | Replace hardcoded colors with theme tokens (FleetColors) | Dashboard, Reports, CostEntry screens | Medium | Dark mode support, dynamic theming, visual consistency
P2 | Internationalize all hardcoded strings | Dashboard, Profile, all Report screens, Maps | High | i18n readiness; AlertsListScreen is the exemplar pattern
P2 | Convert CreateTrip to multi-step wizard | CreateTripScreen | High | Reduce form abandonment on mobile; AddVehicle already has 2-step wizard
P2 | Split VehicleFinance monolithic ViewModel into per-screen VMs | All 4 finance screens | High | Eliminate cross-screen recomposition; clean architecture
P2 | Fix N+1 API query in VehicleFinance (sequential per-vehicle calls) | VehicleFinanceViewModel | Medium | Eliminates slow sequential API calls for large fleets
P3 | Create shared UI components: FleetTopAppBar, FleetFilterChipRow, FleetShimmerPlaceholder | All screens | High | Consistency and reduced boilerplate across 40+ screens
P3 | Adopt ScreenContent<T> wrapper in simpler screens | AlertsList, CustomersList, TeamList | Medium | Reduce manual loading/error/empty branching
P3 | Add shimmer/skeleton loading for data-rich screens | Dashboard, Profile, Detail screens | Medium | Improved perceived performance
P3 | Implement actual Maps integration (Google Maps/MapKit/Leaflet) | MapsScreen | Very High | Core feature (real-time tracking) is non-functional
P3 | Add deep link support for key routes | VehicleDetail, TripDetail, PaymentDetail | High | Enable notification tap-through and link sharing
P3 | Make alert dismiss persistent (server-side or local DB) | AlertsListScreen | Medium | Dismissed alerts won't reappear on refresh
P3 | Add draft saving for CreateTrip form | CreateTripScreen | High | Protect users from data loss on interruptions

## Screen Scorecard
Screen | Loading | Empty | Error | Validation | Navigation | Accessibility | Shared Components | i18n | Overall
LoginScreen | ★★★★ | N/A | ★★★ | ★★ | ★★★★ | ★★★ | ★★★★ | ★★★★ | ★★★
SignUpScreen | ★★★★ | N/A | ★★★ | ★★★ | ★★★★ | ★ | ★★★ | ★★★★ | ★★★
ForgotPasswordScreen | ★★★★ | N/A | ★★★★ | ★★★ | ★★★★ | ★ | ★ | ★★★★ | ★★★
ChangePasswordScreen | ★★★★ | N/A | ★★★★ | ★★★★ | ★★★★ | ★ | ★ | ★★★★ | ★★★
ProfileScreen | ★★ | N/A | ★★★★ | ★★★ | ★★★★ | ★★★ | ★★★★ | ★★ | ★★★
OnboardingScreen | N/A | N/A | N/A | N/A | ★★★★ | ★★★★ | ★★★★ | ★★★★★ | ★★★★
DashboardScreen | ★★★★ | ★★★★★ | ★★★★ | N/A | ★★★★★ | ★★★★ | ★★★★ | ★ | ★★★★
VehiclesListScreen | ★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
AddVehicleScreen | ★★★★ | N/A | ★★★ | ★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
VehicleDetailScreen | ★★★★ | ★★★ | ★★★★ | ★★★ | ★★★★ | ★★ | ★★★★ | ★★★ | ★★★★
MaintenanceCostEntry | ★★★★ | ★★★ | ★★★ | ★★★★ | ★★★ | ★★ | ★★★ | ★★★ | ★★★
DriversListScreen | ★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★ | ★★★★ | ★★★★★ | ★★★★
CreateDriverScreen | ★★★★ | N/A | ★★★ | ★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
DriverDetailScreen | ★★★★ | ★★★★ | ★★★★ | ★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
DriverCostEntryScreen | ★★★★ | ★★★ | ★★★ | ★★★★ | ★★★ | ★★ | ★★★ | ★★★ | ★★★
TripsListScreen | ★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
CreateTripScreen | ★★★★ | N/A | ★★★ | ★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
TripDetailScreen | ★★★★★ | ★★★★★ | ★★★★ | ★★★★ | ★★★★★ | ★★★ | ★★★★ | ★★★★ | ★★★★★
TripCostEntryScreen | ★★★★ | ★★★ | ★★★ | ★★★★ | ★★★ | ★★ | ★★★ | ★★★ | ★★★
CustomersListScreen | ★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★ | ★★ | ★★★★ | ★★★★
CreateCustomerScreen | ★★★★ | N/A | ★★★ | ★★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
CustomerDetailScreen | ★★★★ | ★★★★ | ★★★★ | ★★★★★ | ★★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
PaymentsListScreen | ★★★★★ | ★★★★★ | ★★★★ | N/A | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
AddPaymentScreen | ★★★★ | N/A | ★★★ | ★★★★ | ★★★★ | ★★ | ★★★ | ★★★★ | ★★★
PaymentDetailScreen | ★★★★ | N/A | ★★★★ | N/A | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
TeamListScreen | ★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★★ | ★★★★ | ★★★★ | ★★★★
CreateTeamMemberScreen | ★★★★ | N/A | ★★★ | ★★★ | ★★★★ | ★ | ★★★ | ★★★★ | ★★★
TeamMemberDetailScreen | ★★★★ | N/A | ★★★★ | ★★★★ | ★★★★ | ★★ | ★★★★ | ★★★★ | ★★★★
VehicleFinanceScreen | ★★★★ | ★★★★ | ★★★★ | N/A | ★★★★ | ★★ | ★★★ | ★★★ | ★★★
VehicleFinanceDetail | ★★★★ | ★★★★ | ★★★★ | N/A | ★★★★ | ★★ | ★★★ | ★★★ | ★★★
AddPurchaseInfoScreen | ★★★★ | N/A | ★★★ | ★★★★ | ★★★ | ★★ | ★★★ | ★★★ | ★★★
EmiPaymentHistory | ★★★★ | ★★★★ | ★★★★ | N/A | ★★★ | ★★ | ★★★ | ★★★ | ★★★
ReportsHubScreen | ★★★★ | ★★ | ★★ | N/A | ★★★ | ★★ | ★★ | ★ | ★★
VehicleProfitLossScreen | ★★★★ | ★★★ | ★★ | N/A | ★★★ | ★★ | ★ | ★ | ★★
TripProfitLossScreen | ★★★ | ★★ | ★★ | N/A | ★★★ | ★★ | ★ | ★★ | ★★
CostAnalysisScreen | ★★ | ★ | ★★ | N/A | ★★★ | ★★ | ★ | ★★ | ★★
ConsolidatedPLScreen | ★★ | ★ | ★★ | N/A | ★★★ | ★★ | ★ | ★★ | ★★
MapsScreen | ★ | ★ | ★★★★ | N/A | ★★★ | ★ | ★ | ★★ | ★
AlertsListScreen | ★★★★★ | ★★★★★ | ★★★★★ | N/A | ★★★★ | ★★★★ | ★★★★★ | ★★★★★ | ★★★★★

## Reports Deep-Dive
IndusJS Fleet — Reports Module Deep-Dive UX Enhancement
5 report screens • 19 presentation files (6,946 lines) • 9 API endpoints • 12 PDF export types • Complete functionality, data, flow & UI audit
S.No | Area / Screen | Finding | Severity | Category | Current Behavior | Recommended Enhancement | User Impact | Effort
Reports Hub (9 findings)
1 | Reports Hub | Snackbar effects silently dropped (CRITICAL BUG) | Critical | Bug | Lines 77-78: 'is Effect.ShowSnackbar -> {}' and 'is Effect.ShowExportSuccess/Error -> {}' — all feedback effects consumed but never displayed. No SnackbarHostState wired | Wire SnackbarHostState in Scaffold + LaunchedEffect to display snackbar text from effects. Follow AlertsListScreen pattern | Users get ZERO feedback on export success/failure and any API errors. Critical for a data-heavy reporting screen | Low
2 | Reports Hub | Private ErrorContent duplicates shared component | High | Consistency | ReportsScreen defines its own private ErrorContent composable (line ~158) without using FleetErrorContext or toErrorInfo() | Replace with shared ErrorContent(context = FleetErrorContext.REPORTS, onRetry = ...) from ijs-ui-components-lib | Different error UI styling vs rest of app; loses context-aware error messages | Low
3 | Reports Hub | No empty state when summary is null | High | User Feedback | When API returns null data (period with no activity), screen shows neither loading nor error — just blank space below period chips | Add EmptyContent: 'No financial activity for this period. Try selecting a different date range.' with a CTA to change period | Users think the screen is broken when there's simply no data for selected period | Low
4 | Reports Hub | 4 dead navigation callbacks | Medium | Dead Code | onNavigateToMaintenanceCostReport, onNavigateToTripCostReport, onNavigateToDriverCostReport, onNavigateToCombinedReport all default to {} — no routes exist for these | Either implement these report sub-screens (driver cost report, maintenance cost report) or remove the buttons from the 'Detailed Reports' grid section | Users tap report cards that do nothing — violates 'every tap should have a response' principle | Medium
5 | Reports Hub | Export PDF is a stub | High | Missing Feature | ReportsViewModel.exportToPdf() hardcodes '/sdcard/IndusJSFleet/reports/report.pdf' (Android-only, non-functional). Uses wrong path API | Integrate with ijs-pdf-report module's FleetProfitLossPdfHandler which already exists and generates proper HTML→PDF | Export button appears functional but produces nothing; broken feature promise | Medium
6 | Reports Hub | No period comparison / trend view | Medium | Missing Feature | Reports Hub shows data for ONE period only. No ability to compare current vs previous period | Add a 'vs Previous Period' toggle that shows delta arrows (↑12% or ↓5%) next to Revenue/Expenses/Profit KPIs | Fleet owners can't quickly see if business is improving or declining — fundamental reporting need | High
7 | Reports Hub | Hardcoded Indian Financial Year quarters | Low | Localization | ReportsViewModel calculates Q1=Apr-Jun, Q2=Jul-Sep etc. — correct for India but hardcoded | Extract to FleetDateTime utility with configurable FY start month | Will break if app expands to non-Indian markets | Medium
8 | Reports Hub | Excessive debug logging (29 log statements) | Low | Code Quality | ReportsViewModel has 29 logger.d() calls including response body logging in production code | Gate verbose logging behind a debug flag or reduce to key lifecycle events only | Log pollution in production; potential PII exposure if financial data is logged | Low
9 | Reports Hub | Pie chart not interactive | Low | Data Viz | Expense breakdown pie chart displays data but slices are not tappable | Make pie slices tappable to drill into CostAnalysis for that specific cost type | Missed opportunity for intuitive drill-down from visual to detail | Medium
Vehicle P&L (10 findings)
10 | Vehicle P&L | Massive 2841-line single file | Critical | Maintainability | VehicleProfitLossScreen.kt contains Fleet Overview, Single Vehicle Wizard, Charts, Filter Sheets, Export Dialog, 40+ composables ALL in one file | Decompose into: FleetOverviewContent.kt, SingleVehiclePLContent.kt, VehicleFilterSheet.kt, PLChartComponents.kt, VehiclePLResultCards.kt (5-6 files, ~500 lines each) | Impossible to code review; merge conflicts; compilation slow; developer productivity loss | High
11 | Vehicle P&L | No loading skeleton for fleet overview | High | Perceived Performance | Fleet overview shows basic spinner while loading ALL vehicle P&L data (which can be slow with 50+ vehicles) | Show shimmer skeleton cards (2-3 placeholder vehicle cards + summary card placeholder) during API call | Long blank loading screen for data-intensive fleet overview; poor perceived performance | Medium
12 | Vehicle P&L | Custom LoadingContent reimplemented | Medium | Consistency | Lines ~88: private LoadingContent composable instead of shared LoadingContent from ijs-ui-components-lib | Replace with shared component: LoadingContent(message = stringResource(...)) | Visual inconsistency with other screens' loading states | Low
13 | Vehicle P&L | Emoji-based toolbar actions (🔍 📄) | Medium | Visual Quality | Filter icon uses Text('🔍') and export uses Text('📄') in TopAppBar actions instead of Material Icons | Replace with Icon(Icons.Outlined.FilterList) and Icon(Icons.Outlined.FileDownload) with proper contentDescription | Unprofessional appearance; poor accessibility; inconsistent icon rendering across platforms | Low
14 | Vehicle P&L | No vehicle comparison mode | High | Missing Feature | Fleet overview shows individual vehicle cards but no side-by-side comparison table | Add a comparison view (selectable via ReportViewMode.LIST): table with Vehicle ¦ Revenue ¦ Expense ¦ Profit ¦ Margin columns, sortable by each column header | Fleet owners with 20+ vehicles need quick comparative analysis, not scrolling through individual cards | High
15 | Vehicle P&L | Bar chart has no interaction | Medium | Data Viz | Custom Canvas horizontal bar chart is read-only; no tap to select vehicle | Add tap gesture on bars to select that vehicle and show its detail card or navigate to single-vehicle report | Static chart misses opportunity for interactive data exploration | Medium
16 | Vehicle P&L | Sort/Filter only in fleet overview mode | Medium | Feature Gap | Sort (by profit/revenue/trips) and filter (profitable/loss-making) only work in fleet mode; single vehicle mode has no filters for its trip summary breakdown | Add date range filter + trip status filter to single vehicle P&L results | Can't narrow down single vehicle analysis to specific trips or date ranges | Medium
17 | Vehicle P&L | Recent reports disappear on navigate away | Low | Data Persistence | RecentReport list is stored only in ViewModel state; lost on navigation | Persist recent reports to multiplatform-settings or Room (3-5 items) for quick re-access | Frequently run reports must be re-configured every time | Medium
18 | Vehicle P&L | No CSV/Excel export (only PDF) | Medium | Missing Feature | ReportExportFormat enum defines PDF/CSV/EXCEL but export dialog only generates PDF via VehicleProfitLossPdfHandler | Implement CSV export using kotlinx-serialization CSV or simple StringBuilder with comma-delimited output. Fleet owners need data in spreadsheets for their accountants | Owners can't share raw data with CAs/accountants who need Excel | High
19 | Vehicle P&L | No auto-refresh when data may be stale | Low | Data Freshness | Report data loaded once on screen entry; no stale indicator or auto-refresh prompt | Show 'Data as of [timestamp]' label + subtle refresh prompt after 5 minutes | Stale report data if user returns to screen after making cost/payment entries | Low
Trip P&L (9 findings)
20 | Trip P&L | Nested scrollable containers | High | UX Anti-pattern | Trip list inside LazyColumn uses Column(Modifier.heightIn(max=300.dp).verticalScroll()) — scrollable inside scrollable | Use LazyColumn items() directly for trips OR use a non-scrollable Column with fixed height | Scroll gesture conflicts; users can't reliably scroll the trip list vs the outer page | Low
21 | Trip P&L | Trip list limited to 100 with no pagination | High | Scalability | 'Showing first 100 of X trips' truncation. No 'Load More' or pagination | Implement pagination with 'Load More' button or infinite scroll for trip selection | Fleet with 500+ trips can't access older trips for P&L analysis | Medium
22 | Trip P&L | No step progress indicator | Medium | Visual Guidance | Uses 'Step 1' / 'Step 2' text labels but no visual stepper (progress bar, numbered circles) | Add a horizontal stepper component: (1) Select Dates → (2) Select Trips → (3) View Results, with active/completed/pending states | Users don't know how far they are in the report generation flow | Low
23 | Trip P&L | Sort/filter UI not exposed | High | Missing Feature | TripPLContract has sortOption (6 options: PROFIT, REVENUE, EXPENSES, MARGIN, DATE, TRIP_ID) and plStatusFilter (ALL/PROFITABLE/LOSS_MAKING) but NO UI controls render them | Add sort dropdown + filter chips above trip results: sort by Profit ↕ + filter Profitable/Loss-Making | Results always shown in API order; users can't find most/least profitable trips quickly | Low
24 | Trip P&L | No individual trip drill-down from results | Medium | Navigation | Trip P&L result cards show summary but no way to tap into the full trip detail or its cost breakdown | Add onTripClick callback: navigate to TripDetail screen or expand card to show cost breakdown inline | Users see a trip is unprofitable but can't investigate why without navigating elsewhere | Medium
25 | Trip P&L | ViewModel passed directly to composable | Medium | Architecture | TripPLContent(state, viewModel) takes entire ViewModel; should take lambda callbacks | Refactor to TripPLContent(state, onLoadTrips, onToggleTrip, onGenerateReport, ...) for testability and preview support | Breaks composable preview; tight coupling; hard to unit test UI | Medium
26 | Trip P&L | No date presets for trip selection | Medium | User Flow | Date range selection is manual only (pick start date, pick end date) | Add quick presets: 'Last 7 days', 'This Month', 'Last Month', 'This Quarter' — same as ReportsHub period chips | Extra taps for common date ranges; inconsistent with Reports Hub which has period chips | Low
27 | Trip P&L | No cost breakdown visualization | Medium | Data Viz | Trip P&L results show revenue/expenses/profit numbers but no pie chart or bar chart for cost breakdown | Add a summary pie chart for total cost breakdown across all selected trips + per-trip cost bar in the result card | Missed opportunity to visualize WHERE money is being spent across trips | Medium
28 | Trip P&L | Empty results show only snackbar | Medium | User Feedback | When P&L generation returns empty list, only a snackbar 'No P&L data available' appears and disappears | Show persistent EmptyContent: 'No profit/loss data for selected trips. Trips may not have costs or pricing configured.' with CTA to adjust selection | Transient feedback for an important outcome; user left staring at old UI with no results | Low
Cost Analysis (8 findings)
29 | Cost Analysis | TopAppBar uses primary color (inconsistent) | Medium | Consistency | CostAnalysisScreen uses containerColor = primary while Reports Hub uses default surface | Standardize on surface background matching Reports Hub and Vehicle P&L | Jarring color change when navigating between report sub-screens | Low
30 | Cost Analysis | Static COST_TYPES fallback instead of dynamic | High | Data Accuracy | Cost type chips use hardcoded COST_TYPES list as fallback (fuel, toll, driver_allowance, etc.) instead of fetching from Room-cached /cost-types/trip | Load cost types from CostTypeRepository (already cached in Room from App Init). Show actual available types, not hardcoded assumptions | Users see cost types that may not exist in their data; miss cost types they've actually used | Medium
31 | Cost Analysis | No pie chart for cost breakdown | Medium | Data Viz | Despite Reports Hub using PieChart for expense breakdown, Cost Analysis only shows progress bars | Add PieChart below the total card showing proportional breakdown across cost types — reuse existing PieChart component | Missed opportunity for visual comparison; progress bars are less intuitive for proportional data | Low
32 | Cost Analysis | No monthly trend visualization | High | Missing Feature | API returns monthlyTrend data (month, year, amount, count) per cost type but the screen NEVER displays it | Add a trend section with a simple line/bar chart showing cost trend over months. CostTypeAnalysisDto.monthlyTrend is fetched but unused | Monthly trend is the most actionable insight in cost analysis — users can't see if costs are increasing | High
33 | Cost Analysis | No vehicle breakdown visualization | High | Missing Feature | API returns vehicleBreakdown data (vehicleId, vehicleNumber, amount, count, percentage) per cost type but screen NEVER displays it | Add a 'By Vehicle' section showing which vehicles incur the most of each cost type. CostTypeAnalysisDto.vehicleBreakdown is fetched but unused | Users can't identify which vehicles are cost outliers — defeats the purpose of cost analysis | High
34 | Cost Analysis | No empty state after generation | Medium | User Feedback | When cost analysis returns no results for selected types/dates, screen shows nothing — no empty message | Show EmptyContent: 'No cost data found for selected types and date range' | Users think screen is broken vs understanding there's genuinely no data | Low
35 | Cost Analysis | Date range is optional but behavior unclear | Low | User Flow | If no dates selected, API uses default period. User doesn't know what default period is being used | Show helper text: 'Leave empty to analyze all-time data' or auto-fill with 'Last 30 days' default | Confusing what date range the analysis covers when fields are empty | Low
36 | Cost Analysis | Emoji-to-cost-type mapping duplicated | Low | Code Quality | Both CostTypeChip and CostTypeCard have identical when(costType) → emoji mapping | Extract to a costTypeEmoji(type: String) utility function or map | Code duplication; risk of divergence if new cost types added | Low
Consolidated P&L (8 findings)
37 | Consolidated P&L | Error card renders BELOW results (easily missed) | High | User Feedback | Error card appears at the bottom of LazyColumn after results. If user has scrolled down, they won't see the error from a failed refresh | Show error as a top-of-screen banner (Snackbar or inline card ABOVE results, not below) | Users miss error feedback for failed report regeneration | Low
38 | Consolidated P&L | No pull-to-refresh or refresh button | Medium | Interaction | No way to refresh data once loaded — no toolbar refresh button, no pull-to-refresh, no retry mechanism | Add refresh IconButton in TopAppBar + pull-to-refresh wrapper on LazyColumn | Stale data after making new cost/payment entries; must navigate away and back | Low
39 | Consolidated P&L | Filter UI is overwhelming on mobile | High | Form UX | Filters card shows vehicle chips, cost type chips, group-by radio, and date range ALL visible at once — very tall on mobile | Make filters collapsible/expandable with a summary line ('3 vehicles, 2 cost types, Monthly'). Expand on tap. Or use a BottomSheet for filters | Information overload; users must scroll past filters to see results every time | Medium
40 | Consolidated P&L | Vehicle chips overflow with long reg numbers | Medium | Visual | Vehicle registration numbers like 'MH-12-AB-1234' in chips can overflow LazyRow with no indication of hidden items | Add a count badge '+ N more' after visible chips, or use FlowRow for wrapping. Show 'X of Y vehicles selected' | Users can't tell how many vehicles are selected vs visible | Low
41 | Consolidated P&L | Group-by options hardcoded as strings | Low | Code Quality | groupBy = 'day' ¦ 'week' ¦ 'month' as raw strings in ConsolidatedPLContract | Create GroupByPeriod enum with DAY, WEEK, MONTH values and toApiString() method | Fragile; no compile-time safety; typo risk | Low
42 | Consolidated P&L | Period breakdown trend arrows missing context | Medium | Data Viz | Trend arrows (↑/↓) show on period rows but no tooltip/explanation of what they compare against | Add comparison text: '↑ 12% vs previous month' instead of just an arrow icon | Users see an arrow but don't know the magnitude or baseline of comparison | Low
43 | Consolidated P&L | No date presets for consolidated report | Medium | User Flow | Manual date picking only; no 'This Month', 'This Quarter', 'This Year' shortcuts | Add FleetDateField quick presets matching Reports Hub period chips | Slow report setup; 4+ taps to set date range vs 1 tap for a preset | Low
44 | Consolidated P&L | Vehicle performance cards not tappable | Medium | Navigation | Vehicle summary cards in consolidated report are display-only; no navigation to Vehicle P&L detail | Add onVehicleClick to navigate to VehicleProfitLoss screen with that vehicle pre-selected | Users see a vehicle summary but can't drill into details without manually navigating | Medium
Data & Architecture (6 findings)
45 | Data & Architecture | Repository returns null for all failures (loses error info) | High | Error Handling | ReportsRemoteDataSource returns null on HTTP failure. Repository wraps null as Result.Error('not found'). Original HTTP status/message lost | Return Result.Error with ApiErrorHandler.extractErrorMessage(status, body) including original error context (403=unauthorized, 500=server error, etc.) | All report failures show generic 'Failed to fetch' instead of actionable error messages (e.g., 'Insufficient permissions') | Medium
46 | Data & Architecture | No caching layer for report data | High | Performance | Every report screen makes fresh API calls on each visit. Reports Hub reloads summary on every navigation. Vehicle P&L refetches all vehicles every time | Add in-memory cache with TTL (5 minutes) for PLSummary and vehicle list. Invalidate on cost/payment create. Use MutableStateFlow in repository | Unnecessary API calls on back-navigation; slow report screen reopening | Medium
47 | Data & Architecture | No Use Case layer for complex reports | Medium | Architecture | Use cases are simple pass-through wrappers (invoke() just calls repository). VehiclePLViewModel contains complex report generation logic that should be in use cases | Move report generation logic (date calculations, multi-vehicle aggregation, sorting, filtering) from ViewModel/VehiclePLReportGenerator into dedicated use cases | Business logic in ViewModel violates Clean Architecture; harder to test; can't reuse between ViewModels | High
48 | Data & Architecture | VehiclePLReportGenerator tightly coupled to ViewModel | Medium | Architecture | VehiclePLReportGenerator receives repository directly and returns sealed result types — essentially a use case masquerading as a helper | Formalize as proper GetFleetOverviewUseCase and GetSingleVehiclePLUseCase injected via Metro | Unclear responsibility boundaries; report generation mixed with presentation concerns | Medium
49 | Data & Architecture | Date format inconsistency: DD-MM-YYYY vs YYYY-MM-DD | Medium | Bug Risk | VehiclePLDateCalculator outputs DD-MM-YYYY format. API expects start_date/end_date but format depends on endpoint (some want DD-MM-YYYY, some YYYY-MM-DD) | Centralize all date conversions through FleetDateTime utility. Document expected format per endpoint in ApiConfig | Potential silent date parsing errors where API receives wrong format | Low
50 | Data & Architecture | No role-based access enforcement in module | High | Security | Report screens are accessible without role checks. AGENTS.md says 'Owner/GM only' but no runtime guard exists in ReportsViewModel or any report screen | Check user role on screen init. If Manager/Supervisor, show 'Reports are available for Owner and General Manager roles' message and navigate back | Managers and Supervisors can access financial reports they shouldn't see | Low
PDF Export (5 findings)
51 | PDF Export | No Trip P&L PDF export | High | Missing Feature | ijs-pdf-report has FleetProfitLossPdfHandler and VehicleProfitLossPdfHandler but NO TripProfitLossPdfHandler. TripPLScreen has no export button | Create TripProfitLossPdfHandler + TripProfitLossPdfData in ijs-pdf-report. Add export button to TripPLScreen toolbar | Users can't export trip P&L reports to share with stakeholders | Medium
52 | PDF Export | No Consolidated P&L PDF export | High | Missing Feature | ConsolidatedPLScreen has no export functionality at all. No PDF handler exists for consolidated reports | Create ConsolidatedPLPdfHandler + ConsolidatedPLPdfData. Add export button to toolbar. Include period breakdown + vehicle summary tables | The most comprehensive report can't be exported/shared/printed | Medium
53 | PDF Export | No Cost Analysis PDF export | Medium | Missing Feature | CostAnalysisScreen has no export button. CostAnalysisPdfHandler exists in ijs-pdf-report but is never called from this screen | Wire CostAnalysisPdfHandler to CostAnalysisScreen with export button in toolbar | Existing PDF handler is built but never connected to the UI | Low
54 | PDF Export | CSV/Excel export not implemented | Medium | Missing Feature | ReportExportFormat enum defines CSV and EXCEL formats but zero implementation exists for either | Implement CSV via StringBuilder (simple). For Excel, generate CSV and let user open in Excel. Show format selector in export dialog | Fleet owners need spreadsheet data for accountants/tax filing | High
55 | PDF Export | Export dialog inconsistent across screens | Medium | Consistency | VehiclePLScreen has elaborate export format dialog. ReportsHub calls exportToPdf() directly (stub). Other screens have no export at all | Standardize: all 5 report screens should have identical export flow via shared FleetExportDialog composable | Confusing inconsistency in export availability and interaction | Medium
Cross-Report Flow (5 findings)
56 | Cross-Report Flow | No drill-down navigation between reports | Critical | User Flow | Reports are silos: can't go from Fleet Overview → Vehicle P&L → Trip P&L for that vehicle. Each report starts from scratch | Add navigation callbacks: Fleet vehicle card → VehiclePL(vehicleId). Vehicle trip summary → TripPL(tripId). Cost breakdown type → CostAnalysis(type). ReportHub insight → specific report | Users must manually re-enter parameters when drilling from summary to detail. Defeats the purpose of hierarchical reporting | Medium
57 | Cross-Report Flow | No shared date range across report screens | High | User Flow | Each report screen has its own independent date range state. Switching from ReportsHub (Monthly) to VehiclePL loses the date context | Pass selected period/dateRange as route parameters: FleetRoute.VehicleProfitLoss(startDate?, endDate?). Or use a shared ReportSettingsStore | Users must re-select the same date range on every sub-report screen — 4+ extra taps per drill-down | Medium
58 | Cross-Report Flow | No 'Back to Reports Hub' breadcrumb | Medium | Navigation | Only standard back button exists. No breadcrumb trail (Reports > Vehicle P&L > MH-12-AB-1234) | Add subtitle text in TopAppBar showing navigation path, or add a breadcrumb Row below AppBar | Users lose context of where they are in the reporting hierarchy | Low
59 | Cross-Report Flow | No report favorites/bookmarks | Medium | User Flow | No way to save a commonly-used report configuration (e.g., 'Monthly Vehicle P&L for Top 5 vehicles') | Add 'Save Report' action that persists name + parameters to Room. Show saved reports on Reports Hub as quick-access cards | Fleet owners re-create the same report configuration repeatedly (e.g., every month-end) | High
60 | Cross-Report Flow | Period selection inconsistent across screens | Medium | Consistency | ReportsHub uses ReportPeriod chip bar (8 presets). VehiclePL has its own period chips. TripPL uses manual date pickers. CostAnalysis uses manual dates. ConsolidatedPL uses manual dates | Create shared FleetPeriodSelector composable used across ALL report screens with consistent presets + custom date override | Different date selection UX on every screen; users must relearn each time | Medium
Missing Functionality (8 findings)
61 | Missing Functionality | No Driver Cost Report screen | High | Missing Feature | AGENTS.md mentions 'driver costs' as a report dimension. onNavigateToDriverCostReport callback exists but is dead. API has /drivers/{id}/costs endpoint | Create DriverCostReportScreen: select driver(s) → date range → generate → show earnings, deductions, net per driver with trend | Fleet owners track driver salary/advance/bonus but can't generate reports on it. Major gap for payroll reconciliation | High
62 | Missing Functionality | No Maintenance Cost Report screen | High | Missing Feature | onNavigateToMaintenanceCostReport callback exists but is dead. API has /vehicles/{id}/maintenance-costs endpoint | Create MaintenanceCostReportScreen: select vehicle(s) → date range → generate → show maintenance cost breakdown with trend | No dedicated screen to analyze maintenance spending across fleet over time | High
63 | Missing Functionality | No Payment Collection Report | High | Missing Feature | Payment module has /trip-payments/summary and /trip-payments/tds-report APIs but no report screen uses them in the Reports module | Create PaymentCollectionReport: payment summary by mode, by customer, by period. Wire TDS report for tax compliance | Trip payment summary and TDS report APIs exist but are inaccessible from Reports | High
64 | Missing Functionality | No YoY / MoM comparison anywhere | High | Missing Feature | All reports show absolute numbers for a single period. No comparison view | Add comparison mode: select two periods (e.g., Jan 2026 vs Jan 2025) and show delta columns (Revenue ↑₹15,000 +8%) | Fundamental reporting gap: fleet owners can't assess business trajectory without manual Excel work | Very High
65 | Missing Functionality | No scheduled/recurring report generation | Medium | Missing Feature | Reports are always on-demand. No ability to schedule weekly/monthly report delivery | Add 'Schedule Report' option: frequency (daily/weekly/monthly) + email delivery. Store schedule in backend | Fleet owners want automated month-end reports emailed to them without manual generation | Very High
66 | Missing Functionality | No dashboard widget for quick P&L | Medium | Missing Feature | Dashboard shows cost overview but no P&L summary widget despite the API supporting it | Add a compact P&L card to Dashboard: Revenue ¦ Expenses ¦ Profit with 'View Full Report' CTA navigating to Reports Hub | Financial summary requires navigating to Reports; should be on the primary Dashboard for Owner/GM | Medium
67 | Missing Functionality | No report sharing (WhatsApp/Email/Link) | Medium | Missing Feature | PDF export saves to device but no native sharing integration | After PDF generation, trigger platform share sheet (Android Intent.ACTION_SEND, iOS UIActivityViewController, Web download) | Fleet owners want to WhatsApp reports to partners/accountants | Medium
68 | Missing Functionality | No data export for all trips/vehicles/costs | Medium | Missing Feature | No bulk data export capability for offline analysis | Add 'Export All Data' option in Reports Hub: CSV download of vehicles, trips, costs, payments for a date range | Accountants need raw data dumps for audit/tax purposes | High
Navigation & Discovery (4 findings)
69 | Navigation & Discovery | Report screens not accessible from entity details | High | Navigation | VehicleDetail, TripDetail, DriverDetail have no 'View P&L Report' action. User must go to Reports then re-select the entity | Add 'View P&L' button in VehicleDetail header, TripDetail actions, DriverDetail actions — navigate with entity pre-selected | Many extra navigation steps to see P&L for an entity you're already viewing | Medium
70 | Navigation & Discovery | Reports Hub grid buttons for unimplemented reports | Medium | User Confusion | Detailed Reports grid shows 'Driver Cost Report', 'Maintenance Cost Report', 'Trip Cost Report', 'Combined Report' cards but all are no-ops | Either implement these screens or hide them. If keeping as placeholders, show 'Coming Soon' badge | Users repeatedly tap non-functional report cards; loss of trust | Low
71 | Navigation & Discovery | No report type descriptions on Reports Hub | Low | Discoverability | Report grid cards show only title (Vehicle P&L, Trip P&L, etc.) — no description of what each report contains | Add 1-line subtitle: Vehicle P&L → 'Revenue vs expenses per vehicle'. Trip P&L → 'Profit margin per trip'. Cost Analysis → 'Expense breakdown by type' | New users don't know which report to use for their question | Low
72 | Navigation & Discovery | No contextual help/tooltips on report metrics | Low | Learnability | Financial terms like 'Gross Profit', 'Net Profit', 'Profit Margin', 'Purchase Price vs Selling Value' shown without explanation | Add info icon (ⓘ) next to key metrics with tooltip: 'Gross Profit = Revenue - Direct Costs' etc. | Non-finance users (drivers, supervisors who might see reports) don't understand metrics | Low

## Reports Summary
Report Area | Total | Critical | High | Medium | Low
Reports Hub | 9 | 1 | 3 | 2 | 3
Vehicle P&L | 10 | 1 | 2 | 5 | 2
Trip P&L | 9 | 0 | 3 | 6 | 0
Cost Analysis | 8 | 0 | 3 | 3 | 2
Consolidated P&L | 8 | 0 | 2 | 5 | 1
Data & Architecture | 6 | 0 | 3 | 3 | 0
PDF Export | 5 | 0 | 2 | 3 | 0
Cross-Report Flow | 5 | 1 | 1 | 3 | 0
Missing Functionality | 8 | 0 | 4 | 4 | 0
Navigation & Discovery | 4 | 0 | 1 | 1 | 2
TOTAL | 72